## Directory
System Test - Test Results
Team Name | AlphabitSoup
Project Name | Latham Colonie FD
Client Name | Dr. Rivituso
Directory of Unit Tests (note: this could also be called an Index or a Catalog)
Pass/Fail Status |  | Unit Number | Unit Test Name | Date Last Tested | Comments or brief description | Integrated with these units
F | P | 1 | Login Form | 2015-10-15 | Test to see if there is a login page where a username, password, and submit | Navbar
F | P | 2 | Navbar | 2015-10-15 | Test to see if the navbar appears in the homepage, and we can link to other pages via the navbar | Login Form
F | P | 3 | Draggable | 2015-10-15 | Test to see if an object can be dragged anywhere on the page
F | P | 4 | FF Database | 2015-10-25 | Test to see if information for firefighters can be pulled from the database

## Login Form
Name of Project
Name of User Story | Login Form
Test to see if there is a login page where a username, password, and submit
Test Case
Pass/Fail Status | Test Number | Description | Action to perform test (input) | Steps to be Executed | State Before Test | Expected result | Observed result | Comments | Tested By | Test Date
P | 1.001 | Enter username | Type in username | Click on input field, type in a username | Empty username field | username appears in input field as typed | Username appears as typed in input field |  | Zach Siatkowski | 2015-11-01
P | 1.002 | Enter password | Type in password | Click on input field, type in a password | Empty password field | password appears as bullets when typing so that characters are hidden | password appears as bullets when typing so that characters are hidden |  | Zach Siatkowski | 2015-11-01
P | 1.003 | Sign In button | Click Sign In button | Click Sign In button | Button appears as is on webpage | Clear input fields | Clears input fields | Strictly UI | Zach Siatkowski | 2015-11-01
F | = Unit Summary |  | 100% | passing | 3 | passed |  | Date of last test = |  | 2015-11-01
| 3 | tests |  |  | 0 | failed
Directory Page

## Navbar
Name of User Story | Navbar
Test to see if the navbar appears in the homepage, and we can link to other pages via the navbar
Test Case
Pass/Fail Status | Test Number | Description | Action to perform test (input) | Steps to be Executed | State Before Test | Expected result | Observed result | Comments | Tested By | Test Date
P | 2.001 | NavbarLinks | Click link in Navbar | Click one link in Navbar | User is on any page of the application | Page will reload to the desired link the user clicked on in the navabar | Desired webpage is loaded |  | Allysa Singh | 2015-11-03
P | 2.002 | NavbarLink | Hover link in navbar | Hover over a navbar link | Navbar links have the same color | Color changes on the link when hovering over it in the navbar | Colors change accordingly |  | Allysa Singh | 2015-11-03
F | = Unit Summary |  | 100% | passing | 2 | passed |  | Date of last test = |  | 0
| 2 | tests |  |  | 0 | failed
Directory Page

## Draggable
Name of User Story | Draggable
Test to see if an object can be dragged anywhere on the page
Test Case
Pass/Fail Status | Test Number | Description | Action to perform test (input) | Steps to be Executed | State Before Test | Expected result | Observed result | Comments | Tested By | Test Date
P | 3.001 | Attempted Drag | Click and hold FF object | Move cursor while clicking and holding FF object | No movement of FF object among the screen | FF object can be moved anywhere among the page | FF object can move anywhere |  | Zach Siatkowski | 2015-10-28
P | 3.002 | Attempted Drag Release | Click and Hold FF object | Move curor while clicking and holding FF object, then release | Movement among the screen with a working "drag" | Draggable object stays at the position of mouse relsease | Draggable object stays at the position of mouse relsease |  | Zach Siatkowski | 2015-10-28
F | = Unit Summary |  | 100% | passing | 2 | passed |  | Date of last test = |  | 0
| 2 | tests |  |  | 0 | failed
Directory Page

## FF Database
Name of User Story | FF Database
Test to see if information for firefighters can be pulled from the database
Test Case
Pass/Fail Status | Test Number | Description | Action to perform test (input) | Steps to be Executed | State Before Test | Expected result | Observed result | Comments | Tested By | Test Date
P | 4.001 | Create database | Add sample data | Add data with possible redundancies | No data inputted | No redundant data found | No redundant data found |  | Sean and Tim | 2015-11-04
P | 4.002 | Attempt to add bad data | Attempt to use Cert/ffid that doesn't exist | Inpuit corrupt data | Would allow corrupt data | Error statement | Drop-down fields will not allow corrupt data | Cool effect of phpmyadmin | Tim and Sean | 2015-11-05
\
F | = Unit Summary |  | 100% | passing | 2 | passed |  | Date of last test = |  | 0
| 2 | tests |  |  | 0 | failed
Directory Page