## Directory
System Test - Test Results
Team Name | AlphabitSoup
Project Name | Latham Colonie FD
Client Name | Dr. Rivituso
Directory of Unit Tests
Pass/Fail Status |  | Unit Number | Unit Test Name | Date Last Tested | Comments or brief description | Integrated with these units
P | P | 1 | CMS | 2015-12-12 | Testing to see the login function of the database as well as doing an adding updating and deleting of firefighter information
P | P | 2 | Draggable | 2015-12-12 | Test selection of firefighters based on certification and the dragging of firefighters and their information to and from separate trucks.
P | P | 3 | Emergency Call | 2015-12-10 | Test to if information from emergency call is displayed

## CMS
Name of Project
Name of User Story | CMS
Testing to see the login function of the database as well as doing an adding updating and deleting of firefighter information
Test Case
Pass/Fail Status | Test Number | Description | Action to perform test (input) | Steps to be Executed | State Before Test | Expected result | Observed result | Comments | Tested By | Test Date
P | 1.001 | Enter Username | Type in username | Click on input field and type in username | Null field | Username appears in input field as typed | Username appears in input field as typed | NULL | Tim Kopping | 2015-11-01
P | 1.002 | Enter Password | Type in password | Click on input field and type in password | Null field | Password appears as bullets when typing so that characters are hidden | Password appears as bullets when typing so that characters are hidden | NULL | Cat Kober/Zach Siatkowski | 2015-11-01
P | 1.003 | Login | Valid Login | Type in correct username and password | Null fields | Login successful | Login successful | NULL | Cat Kober/Zach Siatkowski | 2015-11-01
P | 1.004 | Add Firefighter | Add FF Information | Valid firstname, rank, lastname, and certification | Empty | FF added to database | FF added to database | NULL | Cat Kober/Zach Siatkowski | 2015-12-13
P | 1.005 | Delete Firefighter | Delete FF Information | Select dete button next to firefighter that is to be deleted | Null | FF is deleted from database | FF is deleted from database | NULL | Cat Kober/Zach Siatkowski | 2015-12-13
P | 1.006 | Edit Firefighter | Edit FF Information | Select edit button next to firefighter that is to be deleted | Null | FF information is edited within database | FF information is edited within database | NULL | Cat Kober/Zach Siatkowski | 2015-12-13
P | = Unit Summary |  | 150% | passing | 6 | passed |  | Date of last test = |  | 2015-12-13
| 4 | tests |  |  | 0 | failed
Directory Page

## Draggable
Name of User Story | Draggable
Test selection of firefighters based on certification and the dragging of firefighters and their information to and from separate trucks.
Test Case
Pass/Fail Status | Test Number | Description | Action to perform test (input) | Steps to be Executed | State Before Test | Expected result | Observed result | Comments | Tested By | Test Date
P | 2.001 | Choose firefighters | Be able to scroll through different FF certifications to choose which FF to pick up | Click on certification type then choose FF | Undropped box | List of FF with selected certification appears | List of FF with selected certification appears |  | Allysa Singh | 2015-12-12
P | 2.002 | Drag firefighters onto truck | Be able to pick the FF and have them be able to be placed on trucks | Pick FF from certification list and place them on desired truck | Empty Truck | FF dragged to desired truck and stays put | FF dragged to desired truck and stays put |  | Allysa Singh | 2015-12-12
P | = Unit Summary |  | 100% | passing | 2 | passed |  | Date of last test = |  | 12/12/15
| 2 | tests |  |  | 0 | failed
Directory Page

## Emergency Call
Name of User Story | Emergency Call
Test to if information from emergency call is displayed
Test Case
Pass/Fail Status | Test Number | Description | Action to perform test (input) | Steps to be Executed | State Before Test | Expected result | Observed result | Tested By | Test Date
P | 3.001 | Shows emergency call information | Go to the call information page and check to see if static information is there | Call information page | Null | Visually able to see static information | Visually able to see static information | Cat Kober | 2015-12-10
P | = Unit Summary |  | 100% | passing | 1 | passed |  | Date of last test = |  | 2015-12-10
| 1 | tests |  |  | 0 | failed
Directory Page