## Directory
System Test - Test Results
Team Name | AlphabitSoup
Project Name | Latham Colonie FD
Client Name | Dr. Rivituso
Directory of Unit Tests
Pass/Fail Status |  | Unit Number | Unit Test Name | Date Last Tested | Comments or brief description | Integrated with these units
P | P | 1 | Login Secure | 2016-03-28 | Test to see that login in secure and no one can access the application without logging in
P | P | 2 | Apperance | 2016-03-28 | Test to see application is responsive and easy to read, follow, and operate
P | P | 3 | FF Displayed | 2016-03-28 | Test to see that once firetrucks have been submitted, the submitted trucks appear on a different webpage

## Login Secure
Name of Project
Name of User Story | Login Secure
Test to see that login in secure and no one can access the application without logging in
Test Case
Pass/Fail Status | Test Number | Description | Action to perform test (input) | Steps to be Executed | State Before Test | Expected result | Observed result | Comments | Tested By | Test Date
P | 1.001 | Directed to Login | Web application URL into search bar | Enter any of the applications URLs | NULL | Directed to login page | Directed to login page | NULL | Cat Kober | 2016-03-28
P | 1.002 | Enter invalid username/password | Invalid username and password | Enter username and password | Login page form | Error Message | Error Message | NULL | Cat Kober/Zach Siatkowski | 2016-03-28
P | 1.003 | Null username and password | Null usernmane and password | Submit empty login form | Login page form | Error Message | Error Message | NULL | Cat Kober/Zach Siatkowski | 2016-03-28
P | 1.004 | Valid username and password | Enter valid username and password | Enter valid username and password | Login page form | Directed to desired page of application | Directed to desired application page | NULL | Cat Kober/Zach Siatkowski | 2016-03-28
P | = Unit Summary |  | 100% | passing | 4 | passed |  | Date of last test = |  | 3/28/16
| 4 | tests |  |  | 0 | failed
Directory Page

## Appearnace
Name of User Story | Appearance
Test to see application is responsive and easy to read, follow, and operate
Test Case
Pass/Fail Status | Test Number | Description | Action to perform test (input) | Steps to be Executed | State Before Test | Expected result | Observed result | Comments | Tested By | Test Date
P | 2.001 | Pages responsive | Change window size | Change all window sizes | All windows are at the same size and layout is readible | Layout changes according to window size change and maintains readability | Layout changes according to window size change and maintains readability |  | Allysa Singh | 2016-03-28
P | 2.002 | Overall Readability | Perform actions/ forms/ submissions on each page | Perform actions/ forms/ submissions on each page | No forms or submissions made | Forms and submissions made with ease, directions clear if entailed | Forms and submissions made with ease, directions clear if entailed |  | Allysa Singh | 2016-03-28
P | = Unit Summary |  | 100% | passing | 2 | passed |  | Date of last test = |  | 3/28/16
| 2 | tests |  |  | 0 | failed
Directory Page

## FF Displayed
Name of User Story | FF Displayed
Test to see that once firetrucks have been submitted, the submitted trucks appear on a different webpage
Test Case
Pass/Fail Status | Test Number | Description | Action to perform test (input) | Steps to be Executed | State Before Test | Expected result | Observed result | Tested By | Test Date
P | 3.001 | Submit minimum requirements for truck | Submit requirements for truck | Submit at least 4 people including a driver | Truck is empty and no submits have been made | Trucks submitted and a message confirms and trucks are displayed on alternative page | Trucks submitted and a message confirms and trucks are displayed on alternative page | Sean Walsh | 2016-03-28
P | 3.002 | Submit invalid requirements for truck | Submit a truck with less than 4 people or without driver | Submit a truck with less than 4 people or without driver | Truck is empty and no submits have been made | Error message appears that coorelates with the error in either the number of firefighters or no driver | Error message appears that coorelates with the error in either the number of firefighters or no driver | Sean Walsh | 2016-03-30
P | = Unit Summary |  | 100% | passing | 2 | passed |  | Date of last test = |  | 2016-03-28
| 2 | tests |  |  | 0 | failed
Directory Page